## Tasks Codes
New Hampshire Community Technical Assistance Program
CTAP Task Tracking System
Task Code Spreadsheet
Task | Year | Program Name | Notes | Code | Name
C1 | 1 | Local Government Discretionary Accounts |  | C | Central NH RPC
C2 | 1 | Enhanced GIS-Based Information |  | N | Nashua RPC
C3 | 1 | Community Assessments |  | R | Rockingham RPC
C4 | 1 | Connecting Transportation and Land Use |  | S | Southern NH RPC
C5 | 1 | Local Government Cluster Workshops
C6 | 1 | Economic Strategic Planning Inventories
C7 | 1 | Natural Services Implementation
N1 | 1 | Local Government Discretionary Accounts
N2 | 1 | Enhanced GIS-Based Information
N3 | 1 | Community Assessments
N4 | 1 | Connecting Transportation and Land Use
N5 | 1 | External Communication Plan
N6 | 1 | GIS Buildout Analysis and Alternatives
R1 | 1 | Local Government Discretionary Accounts
R2 | 1 | Enhanced GIS-Based Information
R3 | 1 | Community Assessments
R4 | 1 | Connecting Transportation and Land Use
R5 | 1 | Regional Grant Writing Services
S1 | 1 | Local Government Discretionary Accounts
S2 | 1 | Enhanced GIS-Based Information
S3 | 1 | Community Assessments
S4 | 1 | Connecting Transportation and Land Use
S5 | 1 | Conservation Commission Institute
S7 | 1 | Local Open Space Planning

## Summary Sheet
|  | NH CTAP Status Report |  | Period Ending
Task | Year | Title | Budget | Budget Spent | % of Budget Spent | Targeted Completion Date | % Complete
C1 | 1 | Local Government Discretionary Accounts | 75000 | 0 | 0%
C2 | 1 | Enhanced GIS-Based Information | 25000 | 0 | 0%
C3 | 1 | Community Assessments | 25000 | 0 | 0%
C4 | 1 | Connecting Transportation and Land Use | 5000 | 0 | 0%
C5 | 1 | Local Government Cluster Workshops | 28000 | 0 | 0%
C6 | 1 | Economic Strategic Planning Inventories | 10000 | 0 | 0%
C7 | 1 | Natural Services Implementation | 25000 | 0 | 0%
|  | Sub-Total Central NH RPC | 193000 | 0 | 0%
N1 | 1 | Local Government Discretionary Accounts | 45000 | 0 | 0%
N2 | 1 | Enahnced GIS-Based Information | 15000 | 0 | 0%
N3 | 1 | Community Assessments | 15000 | 0 | 0%
N4 | 1 | Connecting Transportation and Land Use | 5000 | 0 | 0%
N5 | 1 | External Communication Plan | 35000 | 0 | 0%
N6 | 1 | GIS Buildout Analysis and Alternatives | 70000 | 0 | 0%
|  | Sub-Total Nashua RPC | 185000 | 0 | 0%
R1 | 1 | Local Government Discretionary Accounts | 105000 | 0 | 0%
R2 | 1 | Enhanced GIS-Based Information | 35000 | 0 | 0%
R3 | 1 | Community Assessments | 35000 | 0 | 0%
R4 | 1 | Connecting Transportation and Land Use | 5000 | 0 | 0%
R5 | 1 | Regional Grant Writing Services | 60000 | 0 | 0%
|  | Sub-Total Rockingham RPC | 240000 | 0 | 0%
S1 | 1 | Local Government Discretionary Accounts | 165000 | 0 | 0%
S2 | 1 | Enhanced GIS-Based Information | 55000 | 0 | 0%
S3 | 1 | Community Assessments | 55000 | 0 | 0%
S4 | 1 | Connecting Transportation and Land Use | 5000 | 0 | 0%
S5 | 1 | Conservation Commission Institute | 25000 | 0 | 0%
S7 | 1 | Local Open Space Planning | 100000 | 0 | 0%
|  | Sub-Total Southern NH RPC | 405000 | 0 | 0%
|  | TOTAL | 1023000 | 0 | 0%

## C1 Y1
Task: C1 Year: 1 |  | Task Title: Local Government Discretionary Accounts
Report Date:
Task Description: The Local Government Discretionary Account is a Year One Program of CTAP intended to help local governments undertake a project that addresses an immediate concern to their community and helps to achieve the broad goals of CTAP.
Task Manager: Sharon Wason |  | Phone: | Email:
Task Contact: |  | Phone: | Email:
Major Deliverables: |  |  |  |  | Total Budget: $75,000 ($15,000/town)
Subtasks
Sub-task # | Title | Sub-Task Objective | Targeted Completion Date | Community Budget | Community Budget Expended to Date | % Completed to Date | % of Community Budget Expended to Date | Actual Completion Date
C1.1 | Allenstown |  |  | 15000 |  |  | 0%
C1.2 | Bow |  |  | 15000 |  |  | 0%
C1.3 | Concord |  |  | 15000 |  |  | 0%
C1.4 | Dunbarton |  |  | 15000 |  |  | 0%
C1.5 | Pembroke |  |  | 15000 |  |  | 0%
C1.5 | Adminstrative Costs | [5 empty] | #DIV/0!
Totals: |  |  |  | 75000 | 0 |  | 0%

## C2 Y1
Task: C2 Year: 1 |  | Title: Enhanced GIS/Land Use Mapping
Report Date:
Task Description:Develop detailed land use coverage for all communities of CTAP
Task Manager: Sharon Wason |  | Phone: | Email:
Task Contact: |  | Phone: | Email:
Major Deliverables: |  |  |  |  | Total Budget: $25,000
Subtasks
Sub-task # | Title | Sub-Task Objective | Targeted Completion Date | Budget | Budget Expended to Date | % Completed to Date | % of Budget Expended to Date | Actual Completion Date
C2.1 | Digital Orthophotography | Acquistion of digital orthophotography | 2006-12-01
C2.2 | Land Use Classification and Coding | Adoption of a land use classification and coding system | 2007-01-01
C2.3 | Training | Provide training to GIS staff members of each RPC | 2007-02-01
C2.4 | Land Use/Land Cover Mapping | Consolidated land use data set for the CTAP study area | 2007-05-01
C2.5 | Map Publication & Distribution | Generation and printing of high quality large format of each CTAP community | 2007-08-01
Totals: |  |  |  | 0 | 0 |  | #DIV/0!

## C3 Y1
Task: C3 Year: 1 |  | Title: Community Assessments
Report Date:
Task Description: The purpose of this task is to develop and complete Community Assessments that will be used to determine what policies, ordinances, regulations, and other procedures currently exist in the 26 CTAP communities
Task Manager: Sharon Wason |  | Phone: | Email:
Task Contact: |  | Phone: | Email:
Major Deliverables: • A printed and electronic Community Assessment Report for the CTAP communities in their region. |  |  |  |  | Total Budget:$25,000 $5,000/town
Subtasks
Sub-task # | Title | Sub-Task Objective | Targeted Completion Date | Budget | Budget Expended to Date | % Completed to Date | % of Budget Expended to Date | Actual Completion Date
C3.1 | Establishment of a Working Group | Develop a survey instrument to conduct the community assessments | 2007-01-07
C3.2 | Establishing Methods and Tools for Conducting the Assessments | A uniform survey instrument for completing the assessment will be finalized. | 2007-02-07
C3.2.1 | Establishment of a consistent survey instrument and methods for conducting the Community Assessment analysis.
C3.2.2 | Consensus reached on a uniform format for completing the assessments.
C3.2.3 | An evaluation of appropriate training needs and necessary training scheduled.
C3.2.4 | Identification of the content and format for a final report to be submitted for each community.
C3.2.5 | Establishment of a community outreach strategy for presenting Community Assessment results.
C3.3 | Training |  | Feb- Mar-07
C3.4 | Community Assessment Analysis |  | Mar-May-07
C3.4.1 | Working Group will review preliminary Community Assessment results for each completed community.
C3.4.2 | Communities will review preliminary results and provide input.
C3.4.3 | Creation of a finalized Community Assessment Analysis report for each community
C3.4.4 | Creation of final summary Regional Assessment report for Steering Committee, Management Committee, and other. |  | Jun-Jul-07
C3.5 | Project Coordination and Administration |  | Jan-Dec-07
Totals: |  |  |  | 0 | 0 |  | #DIV/0!

## C4 Y1
Task: C4 Year: 1 |  | Title: Connecting Transportation and Land Use
Report Date:
Task Description: Assess transportation impacts on existing land use practices, design a methodology to integrate and develop consistency between land use and transportation planning.
Task Manager: Sharon Wason |  | Phone: | Email:
Task Contact: |  | Phone: | Email:
Major Deliverables: |  |  |  |  | Total Budget: $5,000
Subtasks
Sub-task # | Title | Sub-Task Objective | Targeted Completion Date | Budget | Budget Expended to Date | % Completed to Date | % of Budget Expended to Date | Actual Completion Date
Totals: |  |  |  | 0 | 0 |  | #DIV/0!

## C5 Y1
Task: C5 Year: 1 |  | Title: Local Government Cluster Workshops
Report Date:
Task Description: Provide training to local governments in specific area identified and consistent with CTAP objectives.
Task Manager: Sharon Wason |  | Phone: | Email:
Task Contact: |  | Phone: | Email:
Major Deliverables: Training Materials |  |  |  |  | Total Budget: $28,000
Subtasks
Sub-task # | Title | Sub-Task Objective | Targeted Completion Date | Budget | Budget Expended to Date | % Completed to Date | % of Budget Expended to Date | Actual Completion Date
C5.1 | Establishment of a working group
C5.2 | Methodology
C5.3 | Data collection and analysis
C5.4 | Identify speakers and locate places for sessions
C5.5 | Reporting
C5.6 | Project coordination and administration
Totals: |  |  |  | 0 | 0 |  | #DIV/0!

## C6 Y1
Task: C6 Year: 1 |  | Title: Economic Strategic Planning Inventories
Report Date:
Task Description: Formulate a strategic plan for a sustainable regional economy
Task Manager: Sharon Wason |  | Phone: | Email:
Task Contact: |  | Phone: | Email:
Major Deliverables: |  |  |  |  | Total Budget: $10,000
Subtasks
Sub-task # | Title | Sub-Task Objective | Targeted Completion Date | Budget | Budget Expended to Date | % Completed to Date | % of Budget Expended to Date | Actual Completion Date
C6.1 | Establishment of a working group
C6.2 | Review existing surveys and requests
C6.3 | Train the trainers
C6.4 | Identify speakers and locate places for sessions
C6.5 | Evaluate
C6.6 | Project coordination and administration
Totals: |  |  |  | 0 | 0 |  | #DIV/0!

## C7 Y1
Task: C7 Year: 1 |  | Title: Natural Services Implementation
Report Date:
Task Description: Build upon and thus leverage the work already being completed by The Jordan Institute by supporting the completion of the Natural Services Network (NSN). The program will research zoning, regulatory, and voluntary techniques to promote
Task Manager: Sharon Wason |  | Phone: | Email:
Task Contact: |  | Phone: | Email:
Major Deliverables: |  |  |  |  | Total Budget: $25,000
Subtasks
Sub-task # | Title | Sub-Task Objective | Targeted Completion Date | Budget | Budget Expended to Date | % Completed to Date | % of Budget Expended to Date | Actual Completion Date
C7.1
Totals: |  |  |  | 0 | 0 |  | #DIV/0!

## N1 Y1
Task: N1 Year: 1 |  | Title: Local Government Discretionary Accounts
Report Date:
Task Description: The Local Government Discretionary Account is a Year One Program of CTAP intended to help local governments undertake a project that addresses an immediate concern to their community and helps to achieve the broad goals of CTAP.
Task Manager: Steve Williams |  | Phone: | Email:
Task Contact: |  | Phone: | Email:
Major Deliverables: |  |  |  |  | Total Budget: $45,000 ($15,000/town)
Subtasks
Sub-task # | Title | Sub-Task Objective | Targeted Completion Date | Community Budget | Community Budget Expended to Date | % Completed to Date | % of Community Budget Expended to Date | Actual Completion Date
N1.1 | Hudson |  |  | 15000 |  |  | 0%
N1.2 | Litchfield |  |  | 15000 |  |  | 0%
N1.3 | Pelham |  |  | 15000 |  |  | 0%
N1.4 | Adminstrative Costs | [5 empty] | #DIV/0!
Totals: |  |  |  | 45000 | 0 |  | 0%

## N2 Y1
Task: N2 Year: 1 |  | Title: Enhanced GIS/Land Use Mapping
Report Date:
Task Description:Develop detailed land use coverage for all communities of CTAP
Task Manager: Steve Williams |  | Phone: | Email:
Task Contact: |  | Phone: | Email:
Major Deliverables: |  |  |  |  | Total Budget: $15,000
Subtasks
Sub-task # | Title | Sub-Task Objective | Targeted Completion Date | Budget | Budget Expended to Date | % Completed to Date | % of Budget Expended to Date | Actual Completion Date
N2.1 | Digital Orthophotography | Acquistion of digital orthophotography | 2006-12-01
N2.2 | Land Use Classification and Coding | Adoption of a land use classification and coding system | 2007-01-01
N2.3 | Training | Provide training to GIS staff members of each RPC | 2007-02-01
N2.4 | Land Use/Land Cover Mapping | Consolidated land use data set for the CTAP study area | 2007-05-01
N2.5 | Map Publication & Distribution | Generation and printing of high quality large format of each CTAP community | 2007-08-01
Totals: |  |  |  | 0 | 0 |  | #DIV/0!

## N3 Y1
Task: N3 Year: 1 |  | Title: Community Assessments
Report Date:
Task Description: The purpose of this task is to develop and complete Community Assessments that will be used to determine what policies, ordinances, regulations, and other procedures currently exist in the 26 CTAP communities
Task Manager: Steve Willliams |  | Phone: | Email:
Task Contact: |  | Phone: | Email:
Major Deliverables: • A printed and electronic Community Assessment Report for the CTAP communities in their region. |  |  |  |  | Total Budget:$15,000 $5,000/town
Subtasks
Sub-task # | Title | Sub-Task Objective | Targeted Completion Date | Budget | Budget Expended to Date | % Completed to Date | % of Budget Expended to Date | Actual Completion Date
N3.1 | Establishment of a Working Group | Develop a survey instrument to conduct the community assessments | 2007-01-07
N3.2 | Establishing Methods and Tools for Conducting the Assessments | A uniform survey instrument for completing the assessment will be finalized. | 2007-02-07
N3.2.1 | Establishment of a consistent survey instrument and methods for conducting the Community Assessment analysis.
N3.2.2 | Consensus reached on a uniform format for completing the assessments.
N3.2.3 | An evaluation of appropriate training needs and necessary training scheduled.
N3.2.4 | Identification of the content and format for a final report to be submitted for each community.
N3.2.5 | Establishment of a community outreach strategy for presenting Community Assessment results.
N3.3 | Training |  | Feb- Mar-07
N3.4 | Community Assessment Analysis |  | Mar-May-07
N3.4.1 | Working Group will review preliminary Community Assessment results for each completed community.
N3.4.2 | Communities will review preliminary results and provide input.
N3.4.3 | Creation of a finalized Community Assessment Analysis report for each community
N3.4.4 | Creation of final summary Regional Assessment report for Steering Committee, Management Committee, and other. |  | Jun-Jul-07
N3.5 | Project Coordination and Administration |  | Jan-Dec-07
Totals: |  |  |  | 0 | 0 |  | #DIV/0!

## N4 Y1
Task: N4 Year: 1 |  | Title: Connecting Transportation and Land Use
Report Date:
Task Description: Assess transportation impacts on existing land use practices, design a methodology to integrate and develop consistency between land use and transportation planning.
Task Manager: Steve Williams |  | Phone: | Email:
Task Contact: |  | Phone: | Email:
Major Deliverables: |  |  |  |  | Total Budget: $5,000
Subtasks
Sub-task # | Title | Sub-Task Objective | Targeted Completion Date | Budget | Budget Expended to Date | % Completed to Date | % of Budget Expended to Date | Actual Completion Date
N4.1
Totals: |  |  |  | 0 | 0 |  | #DIV/0!

## N5 Y1
Task: N5 Year: 1 |  | Title: External Communications Plan
Report Date:
Task Description: Prepare and begin implementation of a program to communicate to the public and decision makers the impacts of growth in CTAP area communities and the purposes the CTAP program.
Task Manager: Steve Williams |  | Phone: | Email:
Task Contact: |  | Phone: | Email:
Major Deliverables: • The External Communications Plan document • Outreach materials as described above under subtask 7 • Electronic versions of both of the above items. |  |  |  |  | Total Budget: $35,000
Subtasks
Sub-task # | Title | Sub-Task Objective | Targeted Completion Date | Budget | Budget Expended to Date | % Completed to Date | % of Budget Expended to Date | Actual Completion Date
N5.1 | Consultant Selection and Contract Negotiation | Select a consultant for the communications plan | Dec 06 – Feb 07
N5.2 | Identification of Prevailing Attitudes and Beliefs about Growth | Conduct focus group meetings and analyze results | Feb 07 – April 07
N5.3 | Identify Critical CTAP Messages | Identify of critical messages | Feb 07 – April 07
N5.4 | Determine Target Audiences | Identify target audiences | Feb 07 – April 07
N5.5 | Identify Outreach Methods/Media | Find the best suited method to convey CTAP messages | May 07
N5.6 | Development of External Communication Plan | Prepare outreach plan | June 07 – August 07
N5.7 | Outreach Materials | Prepare all necessary materials | June 07 – August 07
N5.8 | Initial Implementation | Implement communications plan | Sept 07
Totals: |  |  |  | 0 | 0 |  | #DIV/0!

## N6 Y1
Task: N6 Year: 1 |  | Title: GIS Buildout Analysis and Alternatives
Report Date:
Task Description: Develop and complete a buildout analysis for all communities in the CTAP region.
Task Manager: Steve Williams |  | Phone: | Email:
Task Contact: |  | Phone: | Email:
Major Deliverables: • A printed and electronic Community Buildout Analysis Report for identified year-one communities in their region. The report will contain GIS data, maps, tables and documentation as identified in Task 6.2.6. |  |  |  |  | Total Budget: $70,000
Subtasks
Sub-task # | Title | Sub-Task Objective | Targeted Completion Date | Budget | Budget Expended to Date | % Completed to Date | % of Budget Expended to Date | Actual Completion Date
N6.1 | Establishment of GIS Buildout Working Group | Create working group of RPC and state agencies | Mar-07 – May-07
N6.2 | Establishing Methods and Tools for Conducting the Buildout Analysis | Finalize a consistent rule-based method for conducting the buildout analysis, which will allow for multiple scenario testing. | Mar-07 – May-07
N6.2.1 | Establishment of a consistent rule-based method for conducting the buildout analysis
N6.2.2 | Consensus reached on a uniform GIS tool for completing the buildout
N6.2.3 | Assess the potential for a parcel based buildout and make a recommendation to the Steering Committee.
N6.2.4 | Identify the indicators, or impacts of buildout, to be calculated and standard methods for deriving each indicator
N6.2.5 | An evaluation of appropriate training needs and the training scheduled. Working Group members responsible for steps in the training process will be identified
N6.2.6 | Identification of the content and format for a final report to be submitted for each community
N6.2.7 | A standard method for conducting alternative land use and regulatory scenarios will be established.
N6.2.8 | A process for identifying the seven communities to be completed in year one will be finalized.
N6.2.9 | Establishment of a community outreach strategy for presenting buildout results.
N6.3 | Training | Provide training to GIS staff of the RPC’s | May-07 – Aug-07
N6.4 | Community Buildout Analysis | Completion of a buildout report for the seven selected communities
N6.4.1 | Working Group will review preliminary Buildout results for each completed community
N6.4.2 | Communities will review preliminary results and provide input |  | Sep-07 – Oct-07
N6.4.3 | Development of alternative scenario analysis will be identified through community and other agency input.
N6.4.4 | Calculate buildout impact indicators using standardized processes established in task 6.2.4.
N6.4.5 | Creation of a finalized Buildout Analysis report for each community
N6.5 | Final Buildout Results Community Outreach | Final Buildout Results Community Outreach | Oct-07– Dec-07
N6.6 | Project Coordination and Administration | Organizing the project | Jan-07 – Dec-07
Totals: |  |  |  | 0 | 0 |  | #DIV/0!

## R1 Y1
Task: R1 Year: 1 |  | Title: Local Government Discretionary Accounts
Report Date:
Task Description: The Local Government Discretionary Account is a Year One Program of CTAP intended to help local governments undertake a project that addresses an immediate concern to their community and helps to achieve the broad goals of CTAP.
Task Manager: Cliff Sinnott |  | Phone: | Email:
Task Contact: |  | Phone: | Email:
Major Deliverables: |  |  |  |  | Total Budget: $105,000 ($15,000/town)
Subtasks
Sub-task # | Title | Sub-Task Objective | Targeted Completion Date | Community Budget | Community Budget Expended to Date | % Completed to Date | % of Community Budget Expended to Date | Actual Completion Date
R1.1 | Atkinson |  |  | 15000 |  |  | 0%
R1.2 | Danville |  |  | 15000 |  |  | 0%
R1.3 | Fremont |  |  | 15000 |  |  | 0%
R1.4 | Hampstead |  |  | 15000 |  |  | 0%
R1.5 | Salem |  |  | 15000 |  |  | 0%
R1.6 | Sandown |  |  | 15000 |  |  | 0%
R1.7 | Windham |  |  | 15000 |  |  | 0%
R1.8 | Adminstrative Costs | [5 empty] | #DIV/0!
Totals: |  |  |  | 105000 | 0 |  | 0%

## R2 Y1
Task: R2 Year: 1 |  | Title: Enhanced GIS/Land Use Mapping
Report Date:
Task Description:Develop detailed land use coverage for all communities of CTAP
Task Manager: Cliff Sinnott |  | Phone: | Email:
Task Contact: |  | Phone: | Email:
Major Deliverables: |  |  |  |  | Total Budget: $35,000
Subtasks
Sub-task # | Title | Sub-Task Objective | Targeted Completion Date | Budget | Budget Expended to Date | % Completed to Date | % of Budget Expended to Date | Actual Completion Date
R2.1 | Digital Orthophotography | Acquistion of digital orthophotography | 2006-12-01
R2.2 | Land Use Classification and Coding | Adoption of a land use classification and coding system | 2007-01-01
R2.3 | Training | Provide training to GIS staff members of each RPC | 2007-02-01
R2.4 | Land Use/Land Cover Mapping | Consolidated land use data set for the CTAP study area | 2007-05-01
R2.5 | Map Publication & Distribution | Generation and printing of high quality large format of each CTAP community | 2007-08-01
Totals: |  |  |  | 0 | 0 |  | #DIV/0!

## R3 Y1
Task: R3 Year: 1 |  | Title: Community Assessments
Report Date:
Task Description: The purpose of this task is to develop and complete Community Assessments that will be used to determine what policies, ordinances, regulations, and other procedures currently exist in the 26 CTAP communities
Task Manager: Cliff Sinnott |  | Phone: | Email:
Task Contact: |  | Phone: | Email:
Major Deliverables: • A printed and electronic Community Assessment Report for the CTAP communities in their region. |  |  |  |  | Total Budget:$35,000 $5,000/town
Subtasks
Sub-task # | Title | Sub-Task ObjeRtive | Targeted Rompletion Date | Budget | Budget Expended to Date | % Rompleted to Date | % of Budget Expended to Date | ARtual Rompletion Date
R3.1 | Establishment of a Working Group | Develop a survey instrument to conduct the community assessments | 2007-01-07
R3.2 | Establishing Methods and Tools for Conducting the Assessments | A uniform survey instrument for completing the assessment will be finalized. | 2007-02-07
R3.2.1 | Establishment of a consistent survey instrument and methods for conducting the Community Assessment analysis.
R3.2.2 | Consensus reached on a uniform format for completing the assessments.
R3.2.3 | An evaluation of appropriate training needs and necessary training scheduled.
R3.2.4 | Identification of the content and format for a final report to be submitted for each community.
R3.2.5 | Establishment of a community outreach strategy for presenting Community Assessment results.
R3.3 | Training |  | Feb- Mar-07
R3.4 | Community Assessment Analysis |  | Mar-May-07
R3.4.1 | Working Group will review preliminary Community Assessment results for each completed community.
R3.4.2 | Communities will review preliminary results and provide input.
R3.4.3 | Creation of a finalized Community Assessment Analysis report for each community
R3.4.4 | Creation of final summary Regional Assessment report for Steering Committee, Management Committee, and other. |  | Jun-Jul-07
R3.5 | Project Coordination and Administration |  | Jan-Dec-07
Totals: |  |  |  | 0 | 0 |  | #DIV/0!

## R4 Y1
Task: R4 Year: 1 |  | Title: Connecting Transportation and Land Use
Report Date:
Task Description: Assess transportation impacts on existing land use practices, design a methodology to integrate and develop consistency between land use and transportation planning.
Task Manager: Cliff Sinnott |  | Phone: | Email:
Task Contact: |  | Phone: | Email:
Major Deliverables: |  |  |  |  | Total Budget: $5,000
Subtasks
Sub-task # | Title | Sub-Task Objective | Targeted Completion Date | Budget | Budget Expended to Date | % Completed to Date | % of Budget Expended to Date | Actual Completion Date
R4.1
Totals: |  |  |  | 0 | 0 |  | #DIV/0!

## R5 Y1
Task: R5 Year: 1 |  | Title: Regional Grant Writing Services
Task Description: Provide grant writing services to the CTAP communities to leverage additional funds to plan and manage for growth
Task Manager: Cliff Sinnott |  | Phone: | Email:
Task Contact: |  | Phone: | Email:
Major Deliverables: • RFP for “Grant Resources Guide” • Grants Workshop agenda, resource materials and speaker presentations. • “Grant Resources Guide for CTAP Communities” published as hardcopy booklet, electronic (PDF) document and webpage or web-compatible document accessible through the CTAP website. • List of prequalified grants consultants, categorized by area of expertise/specialty |  |  |  |  | Total Budget: $60,000
Subtasks
Sub-task # | Title | Sub-Task Objective | Targeted Completion Date | Budget | Budget Expended to Date | % Completed to Date | % of Budget Expended to Date | Actual Completion Date
R5.1 | Grant Resources Guide | Production of a guide of grants available | Feb-Apr 07
R5.2 | Grants Workshop | Presentation of funding sources | Feb-Apr 07
R5.3 | Grants Consulting Services | Initial consulting with each CTAP community | Apr 07
R5.4 | Consultant Prequalification | Identification of qualified grant writing consultants | Feb –Mar 07
R5.5 | Administration | Administration of tasks | Dec 06-May 08
Totals: |  |  |  | 0 | 0 |  | #DIV/0!

## S1 Y1
Task: S1 Year: 1 |  | Title: Local Government Discretionary Accounts
Task Description: The Local Government Discretionary Account is a Year One Program of CTAP intended to help local governments undertake a project that addresses an immediate concern to their community and helps to achieve the broad goals of CTAP.
Task Manager: David Preece |  | Phone: | Email:
Task Contact: |  | Phone: | Email:
Major Deliverables: |  |  |  |  | Total Budget: $165,000 ($15,000/town)
Subtasks
Sub-task # | Title | Sub-Task Objective | Targeted Completion Date | Community Budget | Community Budget Expended to Date | % Completed to Date | % of Community Budget Expended to Date | Actual Completion Date
S1.1 | Auburn |  |  | 15000 |  |  | 0%
S1.2 | Bedford |  |  | 15000 |  |  | 0%
S1.3 | Candia |  |  | 15000 |  |  | 0%
S1.4 | Chester |  |  | 15000 |  |  | 0%
S1.5 | Deerfield |  |  | 15000 |  |  | 0%
S1.6 | Derry |  |  | 15000 |  |  | 0%
S1.7 | Goffstown |  |  | 15000 |  |  | 0%
S1.8 | Londonderry |  |  | 15000 |  |  | 0%
S1.9 | Manchester |  |  | 15000 |  |  | 0%
S1.10 | Raymond |  |  | 15000
S1.11 | Hooksett |  |  | 15000
S1.11 | Adminstrative Costs
Totals: |  |  |  | 165000 | 0 |  | 0%

## S2 Y1
Task: S2 Year: 1 |  | Title: Enhanced GIS/Land Use Mapping
Report Date:
Task Description:Develop detailed land use coverage for all communities of CTAP
Task Manager: David Preece |  | Phone: | Email:
Task Contact: |  | Phone: | Email:
Major Deliverables: |  |  |  |  | Total Budget: $55,000
Subtasks
Sub-task # | Title | Sub-Task Objective | Targeted Completion Date | Budget | Budget Expended to Date | % Completed to Date | % of Budget Expended to Date | Actual Completion Date
S2.1 | Digital Orthophotography | Acquistion of digital orthophotography | 2006-12-01
S2.2 | Land Use Classification and Coding | Adoption of a land use classification and coding system | 2007-01-01
S2.3 | Training | Provide training to GIS staff members of each RPC | 2007-02-01
S2.4 | Land Use/Land Cover Mapping | Consolidated land use data set for the CTAP study area | 2007-05-01
S2.5 | Map Publication & Distribution | Generation and printing of high quality large format of each CTAP community | 2007-08-01
Totals: |  |  |  | 0 | 0 |  | #DIV/0!

## S3 Y1
Task:S3 Year: 1 |  | Title: Community Assessments
Report Date:
Task Description: The purpose of this task is to develop and complete Community Assessments that will be used to determine what policies, ordinances, regulations, and other procedures currently exist in the 26 CTAP communities
Task Manager: David Preece |  | Phone: | Email:
Task Contact: |  | Phone: | Email:
Major Deliverables: • A printed and electronic Community Assessment Report for the CTAP communities in their region. |  |  |  |  | Total Budget:$55,000 $5,000/town
Subtasks
Sub-task # | Title | Sub-Task Objective | Targeted Rompletion Date | Budget | Budget Expended to Date | % Completed to Date | % of Budget Expended to Date | Actual Completion Date
S3.1 | Establishment of a Working Group | Develop a survey instrument to conduct the community assessments | 2007-01-07
S3.2 | Establishing Methods and Tools for Conducting the Assessments | A uniform survey instrument for completing the assessment will be finalized. | 2007-02-07
S3.2.1 | Establishment of a consistent survey instrument and methods for conducting the Community Assessment analysis.
S3.2.2 | Consensus reached on a uniform format for completing the assessments.
S3.2.3 | An evaluation of appropriate training needs and necessary training scheduled.
S3.2.4 | Identification of the content and format for a final report to be submitted for each community.
S3.2.5 | Establishment of a community outreach strategy for presenting Community Assessment results.
S3.3 | Training |  | Feb- Mar-07
S3.4 | Community Assessment Analysis |  | Mar-May-07
S3.4.1 | Working Group will review preliminary Community Assessment results for each completed community.
S3.4.2 | Communities will review preliminary results and provide input.
S3.4.3 | Creation of a finalized Community Assessment Analysis report for each community
S3.4.4 | Creation of final summary Regional Assessment report for Steering Committee, Management Committee, and other. |  | Jun-Jul-07
S3.5 | Project Coordination and Administration |  | Jan-Dec-07
Totals: |  |  |  | 0 | 0 |  | #DIV/0!

## S4 Y1
Task: S4 Year: 1 |  | Title: Connecting Transportation and Land Use
Report Date:
Task Description: Assess transportation impacts on existing land use practices, design a methodology to integrate and develop consistency between land use and transportation planning.
Task Manager: David Preece |  | Phone: | Email:
Task Contact: |  | Phone: | Email:
Major Deliverables: |  |  |  |  | Total Budget: $5,000
Subtasks
Sub-task # | Title | Sub-Task Objective | Targeted Completion Date | Budget | Budget Expended to Date | % Completed to Date | % of Budget Expended to Date | Actual Completion Date
S4.1
Totals: |  |  |  | 0 | 0 |  | #DIV/0!

## S5 Y1
Task: S5 Year: 1 |  | Title: Conservation Commission Institute
Reporting Date:
Task Description: Establish a Conservation Commission Institute which will provide ongoing education and training support to conservation commissions in the 26 municipalities within the I-93 corridor.
Task Manager: David Preece |  | Phone: | Email:
Task Contact: |  | Phone: | Email:
Major Deliverables: • Background Information for each meeting • Survey Report • Syllabus and Meeting Calendar • Summary Report of each meeting • Training Materials • DVD and/or Video of each meeting |  |  |  |  | Total Budget: $25,000
Subtasks
Sub-task # | Title | Sub-Task Objective | Targeted Completion Date | Budget | Budget Expended to Date | % Completed to Date | % of Budget Expended to Date | Actual Completion Date
S5.1 | Establishment of Conservation Commission Institute | Create the conservation commission institute for each RPC | Feb 07 – March 07
S5.2 | Survey and Collect Information | Survey the needs of each commission and analyze survey results. Create calendar. | March 07 – April 07
S5.3 | Develop Training Materials | Create and distribute training materials | April 07 – May 07
S5.4 | Organize and Facilitate Meetings |  | May 07 – Dec 07
S5.5 | Project Coordination and Administration
Totals: |  |  |  | 0 | 0 |  | #DIV/0!

## S7 Y1
Task: S7 Year: 1 |  | Title: Local Open Space Planning
Reporting Date:
Task Description: Assist towns with developing or updating their local open space plans using a consistent approach and using new data and analysis.
Task Manager: David Preece |  | Phone: | Email:
Task Contact: |  | Phone: | Email:
Major Deliverables: |  |  |  |  | Total Budget: $100,000 $10,000/town
Subtasks
Sub-task # | Title | Sub-Task Objective | Targeted Completion Date | Budget | Budget Expended to Date | % Completed to Date | % of Budget Expended to Date | Actual Completion Date
S7.1
Totals: |  |  |  | 0 | 0 |  | #DIV/0!