## Tasks Codes
Rockingham Regional Planning Commission
New Hampshire Community Technical Assistance Program
CTAP Task Tracking System
Task Code Spreadsheet
Task | Year | Program Name | Notes | Code | Name
C1 | 1 | Local Government Discretionary Accounts |  | C | Central NH RPC
C2 | 1 | Enhanced GIS-Based Information |  | N | Nashua RPC
C3 | 1 | Community Assessments |  | R | Rockingham RPC
C4 | 1 | Connecting Transportation and Land Use |  | S | Southern NH RPC
C5 | 1 | Local Government Cluster Workshops
C6 | 1 | Economic Strategic Planning Inventories
C7 | 1 | Natural Services Implementation
N1 | 1 | Local Government Discretionary Accounts
N2 | 1 | Enhanced GIS-Based Information
N3 | 1 | Community Assessments
N4 | 1 | Connecting Transportation and Land Use
N5 | 1 | External Communication Plan
N6 | 1 | GIS Buildout Analysis and Alternatives
R1 | 1 | Local Government Discretionary Accounts
R2 | 1 | Enhanced GIS-Based Information
R3 | 1 | Community Assessments
R4 | 1 | Connecting Transportation and Land Use
R5 | 1 | Regional Grant Writing Services
S1 | 1 | Local Government Discretionary Accounts
S2 | 1 | Enhanced GIS-Based Information
S3 | 1 | Community Assessments
S4 | 1 | Connecting Transportation and Land Use
S5 | 1 | Conservation Commission Institute
S7 | 1 | Local Open Space Planning

## R1 Y1
Task: R1 Year: 1 |  | Title: Local Government Discretionary Accounts
Report Date:
Task Description: The Local Government Discretionary Account is a Year One Program of CTAP intended to help local governments undertake a project that addresses an immediate concern to their community and helps to achieve the broad goals of CTAP.
Task Manager: Cliff Sinnott |  | Phone: | Email:
Task Contact: |  | Phone: | Email:
Major Deliverables: |  |  |  |  | Total Budget: $105,000 ($15,000/town)
Subtasks
Sub-task # | Title | Sub-Task Objective | Targeted Completion Date | Community Budget | Community Budget Expended to Date | % Completed to Date | % of Community Budget Expended to Date | Actual Completion Date
R1.1 | Atkinson |  |  | 15000 |  |  | 0%
R1.2 | Danville |  |  | 15000 |  |  | 0%
R1.3 | Fremont |  |  | 15000 |  |  | 0%
R1.4 | Hampstead |  |  | 15000 |  |  | 0%
R1.5 | Salem |  |  | 15000 |  |  | 0%
R1.6 | Sandown |  |  | 15000 |  |  | 0%
R1.7 | Windham |  |  | 15000 |  |  | 0%
R1.8 | Adminstrative Costs | [5 empty] | #DIV/0!
Totals: |  |  |  | 105000 | 0 |  | 0%

## R2 Y1
Task: R2 Year: 1 |  | Title: Enhanced GIS/Land Use Mapping
Report Date:
Task Description:Develop detailed land use coverage for all communities of CTAP
Task Manager: Cliff Sinnott |  | Phone: | Email:
Task Contact: |  | Phone: | Email:
Major Deliverables: |  |  |  |  | Total Budget: $35,000
Subtasks
Sub-task # | Title | Sub-Task Objective | Targeted Completion Date | Budget | Budget Expended to Date | % Completed to Date | % of Budget Expended to Date | Actual Completion Date
R2.1 | Digital Orthophotography | Acquistion of digital orthophotography | 2006-12-01
R2.2 | Land Use Classification and Coding | Adoption of a land use classification and coding system | 2007-01-01
R2.3 | Training | Provide training to GIS staff members of each RPC | 2007-02-01
R2.4 | Land Use/Land Cover Mapping | Consolidated land use data set for the CTAP study area | 2007-05-01
R2.5 | Map Publication & Distribution | Generation and printing of high quality large format of each CTAP community | 2007-08-01
Totals: |  |  |  | 0 | 0 |  | #DIV/0!

## R3 Y1
Task: R3 Year: 1 |  | Title: Community Assessments
Report Date:
Task Description: The purpose of this task is to develop and complete Community Assessments that will be used to determine what policies, ordinances, regulations, and other procedures currently exist in the 26 CTAP communities
Task Manager: Cliff Sinnott |  | Phone: | Email:
Task Contact: |  | Phone: | Email:
Major Deliverables: • A printed and electronic Community Assessment Report for the CTAP communities in their region. |  |  |  |  | Total Budget:$35,000 $5,000/town
Subtasks
Sub-task # | Title | Sub-Task ObjeRtive | Targeted Rompletion Date | Budget | Budget Expended to Date | % Rompleted to Date | % of Budget Expended to Date | ARtual Rompletion Date
R3.1 | Establishment of a Working Group | Develop a survey instrument to conduct the community assessments | 2007-01-07
R3.2 | Establishing Methods and Tools for Conducting the Assessments | A uniform survey instrument for completing the assessment will be finalized. | 2007-02-07
R3.2.1 | Establishment of a consistent survey instrument and methods for conducting the Community Assessment analysis.
R3.2.2 | Consensus reached on a uniform format for completing the assessments.
R3.2.3 | An evaluation of appropriate training needs and necessary training scheduled.
R3.2.4 | Identification of the content and format for a final report to be submitted for each community.
R3.2.5 | Establishment of a community outreach strategy for presenting Community Assessment results.
R3.3 | Training |  | Feb- Mar-07
R3.4 | Community Assessment Analysis |  | Mar-May-07
R3.4.1 | Working Group will review preliminary Community Assessment results for each completed community.
R3.4.2 | Communities will review preliminary results and provide input.
R3.4.3 | Creation of a finalized Community Assessment Analysis report for each community
R3.4.4 | Creation of final summary Regional Assessment report for Steering Committee, Management Committee, and other. |  | Jun-Jul-07
R3.5 | Project Coordination and Administration |  | Jan-Dec-07
Totals: |  |  |  | 0 | 0 |  | #DIV/0!

## R4 Y1
Task: R4 Year: 1 |  | Title: Connecting Transportation and Land Use
Report Date:
Task Description: Assess transportation impacts on existing land use practices, design a methodology to integrate and develop consistency between land use and transportation planning.
Task Manager: Cliff Sinnott |  | Phone: | Email:
Task Contact: |  | Phone: | Email:
Major Deliverables: |  |  |  |  | Total Budget: $5,000
Subtasks
Sub-task # | Title | Sub-Task Objective | Targeted Completion Date | Budget | Budget Expended to Date | % Completed to Date | % of Budget Expended to Date | Actual Completion Date
R4.1
Totals: |  |  |  | 0 | 0 |  | #DIV/0!

## R5 Y1
Task: R5 Year: 1 |  | Title: Regional Grant Writing Services
Task Description: Provide grant writing services to the CTAP communities to leverage additional funds to plan and manage for growth
Task Manager: Cliff Sinnott |  | Phone: | Email:
Task Contact: |  | Phone: | Email:
Major Deliverables: • RFP for “Grant Resources Guide” • Grants Workshop agenda, resource materials and speaker presentations. • “Grant Resources Guide for CTAP Communities” published as hardcopy booklet, electronic (PDF) document and webpage or web-compatible document accessible through the CTAP website. • List of prequalified grants consultants, categorized by area of expertise/specialty |  |  |  |  | Total Budget: $60,000
Subtasks
Sub-task # | Title | Sub-Task Objective | Targeted Completion Date | Budget | Budget Expended to Date | % Completed to Date | % of Budget Expended to Date | Actual Completion Date
R5.1 | Grant Resources Guide | Production of a guide of grants available | Feb-Apr 07
R5.2 | Grants Workshop | Presentation of funding sources | Feb-Apr 07
R5.3 | Grants Consulting Services | Initial consulting with each CTAP community | Apr 07
R5.4 | Consultant Prequalification | Identification of qualified grant writing consultants | Feb –Mar 07
R5.5 | Administration | Administration of tasks | Dec 06-May 08
Totals: |  |  |  | 0 | 0 |  | #DIV/0!